## Project Information
I. Requirements
XÂY DỰNG HỆ THỐNG QUẢN LÝ ĐỌC TRUYỆN Admin có thể tạo và quản lý các bộ truyện được phát hành trên hệ thống. Mỗi truyện có các thông tin cơ bản như tên truyện, ảnh bìa, giới thiệu nội dung, tác giả, thể loại, tình trạng phát hành và các thông tin mô tả cần thiết khác. Một truyện có thể thuộc một hoặc nhiều thể loại để hỗ trợ việc phân loại, tìm kiếm và giới thiệu nội dung đến người đọc. Mỗi bộ truyện bao gồm nhiều chương. Sau khi tạo truyện, Admin có thể tạo hoặc tải lên các chương của truyện, xác định số thứ tự chương, tên chương, nội dung và thời điểm phát hành. Các chương có thể được chuẩn bị trước và công bố vào thời điểm phù hợp. Trong quá trình vận hành, Admin có thể chỉnh sửa thông tin truyện hoặc nội dung từng chương khi phát hiện sai sót hoặc cần cập nhật. Admin có thể thiết lập chính sách truy cập cho từng bộ truyện: hoàn toàn miễn phí, hoàn toàn trả phí hoặc kết hợp. Với truyện trả phí, Admin có thể chọn một số chương đọc miễn phí (ví dụ các chương đầu) để giới thiệu nội dung; các chương còn lại chỉ truy cập được khi thành viên có quyền đọc hợp lệ. Người đọc có thể xem trang thông tin truyện (ảnh bìa, tên, giới thiệu, tác giả, thể loại, tình trạng phát hành, danh sách chương kèm trạng thái truy cập), tìm kiếm truyện theo tên/tác giả/thể loại, và duyệt các danh sách như truyện mới cập nhật, mới phát hành, được đọc nhiều... Đối với chương trả phí, hệ thống kiểm tra quyền đọc của thành viên trước khi cho phép truy cập, thông qua: (1) gói đọc theo tháng còn hiệu lực, hoặc (2) đã mua riêng bộ truyện đó. Admin quản lý các gói đọc theo tháng (tên gói, mức phí, thời hạn, phạm vi nội dung) và mức phí của từng truyện trả phí. Nếu thành viên có cả hai quyền, hệ thống xác định quyền truy cập hợp lý để không thu phí trùng. Mọi giao dịch đăng ký gói/mua truyện được ghi nhận; thành viên xem được lịch sử thanh toán, gói đang dùng, ngày bắt đầu/hết hạn. Giao dịch thất bại thì quyền đọc không kích hoạt; nếu thanh toán thành công nhưng cập nhật quyền lỗi thì hệ thống cần kiểm tra và xử lý để đảm bảo quyền lợi thành viên. Hệ thống ghi nhận tiến độ đọc để thành viên tiếp tục đọc từ vị trí gần nhất; thành viên có thể theo dõi truyện đang đọc, đã mua, quan tâm/yêu thích, và nhận thông báo khi truyện theo dõi có chương mới. Mỗi chương có khu vực thảo luận riêng để thành viên đăng bình luận, trao đổi. Admin theo dõi, kiểm duyệt nội dung vi phạm/spam và xử lý tài khoản vi phạm; Admin cũng quản lý danh sách thành viên, có thể hạn chế/tạm ngừng tài khoản vi phạm. Admin cập nhật trạng thái truyện (đang phát hành/đã hoàn thành) khi có chương mới hoặc truyện kết thúc. Hệ thống ghi nhận số lượt đọc theo truyện/chương để phục vụ thống kê. Admin có thể thống kê: số lượng thành viên, số đang dùng gói tháng, số đăng ký mới, số lượt gia hạn, số lượt mua truyện, tình trạng giao dịch; doanh thu gói đọc theo tháng (số gói bán, gia hạn, doanh thu theo gói/thời gian); doanh thu mua truyện (lượt mua, doanh thu từng truyện, tổng doanh thu theo thời gian); và các thống kê nội dung (truyện đọc nhiều nhất, nhiều người theo dõi, nhiều lượt mua, chương nhiều lượt đọc/thảo luận, thể loại được quan tâm nhiều). YÊU CẦU KỸ THUẬT: Hệ thống theo kiến trúc client–server, backend cung cấp RESTful API dùng chung cho Web Application và Mobile Application. Web application cung cấp đầy đủ chức năng cho mọi người dùng hệ thống; Mobile application cung cấp chức năng cho phía user/khách hàng (đọc truyện, mua gói/mua truyện, theo dõi, thảo luận).

## Team
TEAM DEVELOPMENT STRUCTURE
No. | Name | Account | Roles | DateStart | Date End
1 | Hồ Anh Kha | https://github.com/Kha206 | Product Owner, Dev | 2026-10-09 | 2026-07-10
2 | Bùi Phước Tính | https://github.com/samsungj87078-jpg | ScrumMaster, Dev | 2026-10-09 | 2026-07-10

## Product backlog
STORY READER PROJECT - PRODUCT BACKLOG
Story ID | Story Name | Points
Actor: là Admin, tôi muốn
1 | Manage Story Information (Create, Edit) | 5
2 | Manage Story Genres (Assign Multiple Genres) | 3
3 | Manage Chapters (Create, Upload, Edit, Schedule Release) | 8
4 | Manage Story Access Policy (Free / Paid / Mixed) | 5
5 | Manage Free Preview Chapters for Paid Story | 3
6 | Manage Monthly Subscription Packages (Create, Update, Discontinue) | 5
7 | Manage Story Price (Set / Adjust) | 3
8 | Manage Transaction & Access-Right Error Handling | 5
9 | Moderate Discussion Content (Handle Reports, Violations) | 5
10 | Manage Member Accounts (View, Restrict, Suspend) | 3
11 | Update Story Status (Ongoing / Completed) | 2
12 | View Read-Count Statistics (Story & Chapter) | 3
13 | View Monthly-Subscription Revenue Statistics | 5
14 | View Story-Purchase Revenue Statistics | 5
15 | View Content Ranking Statistics (Most Read, Most Followed, Most Purchased, Most Discussed, Popular Genres) | 5
16 | View Member & Transaction Statistics | 3
Actor: là khách vãng lai (chưa đăng nhập), tôi muốn
17 | View Story Detail Page | 2
18 | View Chapter List with Access Status | 2
19 | Search Story (by Name, Author, Genre) | 3
20 | Browse Story Lists (New, Latest, Most Read) | 3
Actor: là thành viên (đã đăng ký), tôi muốn
21 | Register | 2
22 | Login | 1
23 | Logout | 1
24 | Read Paid Chapter (with Access-Right Check) | 5
25 | Subscribe Monthly Package (Select & Pay) | 5
26 | Renew Monthly Package | 3
27 | View Active Package Status | 2
28 | Purchase Story (One-time Payment) | 5
29 | View Purchased Story List | 2
30 | View Payment / Transaction History | 3
31 | Track & Resume Reading Progress | 5
32 | View Currently-Reading List | 2
33 | Follow / Favorite Story | 2
34 | Receive New-Chapter Notification | 3
35 | Post Discussion Comment per Chapter | 3
36 | View & Participate in Chapter Discussion | 2
| TOTAL POINTS | 124

## Sprint backlog
STORY READER PROJECT - SPRINT BACKLOG
Story ID | Story Name | Points | Name Of Dev | Start Date | Endate | Act Start Date | ActEndate | Act Points | Notes
Sprint 1
1 | Manage Story Information (Create, Edit) | 5 | Hồ Anh Kha | 10/09/2026 | 16/09/2026
2 | Manage Story Genres (Assign Multiple Genres) | 3 | Bùi Phước Tính | 10/09/2026 | 16/09/2026
3 | Manage Chapters (Create, Upload, Edit, Schedule Release) | 8 | Hồ Anh Kha | 10/09/2026 | 16/09/2026
21 | Register | 2 | Bùi Phước Tính | 10/09/2026 | 16/09/2026
22 | Login | 1 | Hồ Anh Kha | 10/09/2026 | 16/09/2026
23 | Logout | 1 | Bùi Phước Tính | 10/09/2026 | 16/09/2026
17 | View Story Detail Page | 2 | Hồ Anh Kha | 10/09/2026 | 16/09/2026
18 | View Chapter List with Access Status | 2 | Bùi Phước Tính | 10/09/2026 | 16/09/2026
19 | Search Story (by Name, Author, Genre) | 3 | Hồ Anh Kha | 10/09/2026 | 16/09/2026
20 | Browse Story Lists (New, Latest, Most Read) | 3 | Bùi Phước Tính | 10/09/2026 | 16/09/2026
| Sprint 1 Total Points | 30
Sprint 2
4 | Manage Story Access Policy (Free / Paid / Mixed) | 5 | Hồ Anh Kha | 17/09/2026 | 23/09/2026
5 | Manage Free Preview Chapters for Paid Story | 3 | Bùi Phước Tính | 17/09/2026 | 23/09/2026
6 | Manage Monthly Subscription Packages (Create, Update, Discontinue) | 5 | Hồ Anh Kha | 17/09/2026 | 23/09/2026
7 | Manage Story Price (Set / Adjust) | 3 | Bùi Phước Tính | 17/09/2026 | 23/09/2026
24 | Read Paid Chapter (with Access-Right Check) | 5 | Hồ Anh Kha | 17/09/2026 | 23/09/2026
25 | Subscribe Monthly Package (Select & Pay) | 5 | Bùi Phước Tính | 17/09/2026 | 23/09/2026
27 | View Active Package Status | 2 | Hồ Anh Kha | 17/09/2026 | 23/09/2026
26 | Renew Monthly Package | 3 | Bùi Phước Tính | 17/09/2026 | 23/09/2026
| Sprint 2 Total Points | 31
Sprint 3
28 | Purchase Story (One-time Payment) | 5 | Hồ Anh Kha | 24/09/2026 | 30/09/2026
29 | View Purchased Story List | 2 | Bùi Phước Tính | 24/09/2026 | 30/09/2026
30 | View Payment / Transaction History | 3 | Hồ Anh Kha | 24/09/2026 | 30/09/2026
8 | Manage Transaction & Access-Right Error Handling | 5 | Bùi Phước Tính | 24/09/2026 | 30/09/2026
31 | Track & Resume Reading Progress | 5 | Hồ Anh Kha | 24/09/2026 | 30/09/2026
32 | View Currently-Reading List | 2 | Bùi Phước Tính | 24/09/2026 | 30/09/2026
33 | Follow / Favorite Story | 2 | Hồ Anh Kha | 24/09/2026 | 30/09/2026
34 | Receive New-Chapter Notification | 3 | Bùi Phước Tính | 24/09/2026 | 30/09/2026
11 | Update Story Status (Ongoing / Completed) | 2 | Hồ Anh Kha | 24/09/2026 | 30/09/2026
12 | View Read-Count Statistics (Story & Chapter) | 3 | Bùi Phước Tính | 24/09/2026 | 30/09/2026
| Sprint 3 Total Points | 32
Sprint 4
9 | Moderate Discussion Content (Handle Reports, Violations) | 5 | Hồ Anh Kha | 01/10/2026 | 07/10/2026
10 | Manage Member Accounts (View, Restrict, Suspend) | 3 | Bùi Phước Tính | 01/10/2026 | 07/10/2026
13 | View Monthly-Subscription Revenue Statistics | 5 | Hồ Anh Kha | 01/10/2026 | 07/10/2026
14 | View Story-Purchase Revenue Statistics | 5 | Bùi Phước Tính | 01/10/2026 | 07/10/2026
15 | View Content Ranking Statistics (Most Read, Most Followed, Most Purchased, Most Discussed, Popular Genres) | 5 | Hồ Anh Kha | 01/10/2026 | 07/10/2026
16 | View Member & Transaction Statistics | 3 | Bùi Phước Tính | 01/10/2026 | 07/10/2026
35 | Post Discussion Comment per Chapter | 3 | Hồ Anh Kha | 01/10/2026 | 07/10/2026
36 | View & Participate in Chapter Discussion | 2 | Bùi Phước Tính | 01/10/2026 | 07/10/2026
| Sprint 4 Total Points | 31